## Accounts & Contacts
User Story ID | Theme | As a(n)... | I want to... | So that I can... | Acceptance Criteria | Priority | Type | LOE | Sprint
|  | AAFP Staff | Create a New Account | capture new organizations that have a relationship with AAFP | Open the Account tab, click the new Button, enter contact details, and click Save | High | Configuration
|  | AAFP Admin | Create custom fields on Account | capture information relevant to an organization at AAFP | The following fields are captured: on the account record - see attached reference document | High | Configuration
|  | AAFP Staff | Create a New Contact | capture new individuals that have a relationship with AAFP | Open the Contact tab, click the new Button, enter contact details, and click Save | High | Configuration
|  | AAFP Admin | Create custom fields on Contact | capture information relevant to an individual at AAFP | The following fields are captured: on the contact record - see attached reference document | High | Configuration
|  | AAFP Admin | Update Account and/or Contact Page Layouts | provide relevant information to AAFP users | Only specified admins can navigate to setup in the object manager and customize the page layouts for accounts and contacts | High | Configuration
|  | AAFP Admin | Create Organization-Wide List Views of Accounts and Contacts | Quickly filter information relevant to all staff | To be determined by AAFP | High | Configuration
|  | AAFP Admin | Update the fields displayed on the Member Profile Page | provide relevant information for AAFP members and customers to manage their contact information | Can add fields to the field set on the Member Profile Page | High | Configuration
|  | AAFP Staff | Input country and state from a picklist on the account record with depdendencies between the two fields | capture the appropriate address information | A picklist field for Country and State exist on the Account record and a field dependency exists such that when a user selects a country value, a filtered list of states will display | High | Configuration
|  | AAFP Staff | Input country and state from a picklist on the contact record with depdendencies between the two fields | capture the appropriate address information | A picklist field for Country and State exist on the Contact record and a field dependency exists such that when a user selects a country value, a filtered list of states will display | High | Configuration
|  | AAFP Staff | View Latitude and Longitude information for the primary contact address | report on geo-location of contacts | CDYNE has pulled in latitude, longitude, and Congressional distrcit of the contact record | Medium | Integration
|  | AAFP Staff | View Latitude and Longitude information for the primary organization address | report on geo-location of organizations | CDYNE has pulled in latitude, longitude, and Congressional distrcit of the account record | Medium | Integration
|  | AAFP Staff | track the role of Contacts with primary and secondary organizations | quickly identify the roles of contacts at different organizations |  | High | Configuration
|  | AAFP Staff | track the level of engagement of a contact | quantify the activity of a customer | To be determined by AAFP | Low | Configuration
|  | AAFP Staff | track the history of organization changes over time | review historical information on an organization | Can view a related list named Account History that tracks the changes of Account Name, etc | High | Configuration
|  | AAFP Staff | Track the history of contact changes over time | review historical information on a contact | Can view a related list named Contact History that tracks the changes of Account, Name, Email, etc. | High | Configuration
|  | AAFP Staff | View the work and home address of a contact | track the appropriate address for a contact | Navigate to a Contact Record and find the Home Address and Other Address fields | High | Configuration
|  | AAFP Staff | View the work and home address of an account | track the appropriate address for an account | Navigate to an Account Record and find the Billing Address and Shipping Address fields | High | Configuration
|  | AAFP Staff | View oustanding dues balance | track any pending dues for a member | To be determined by AAFP | ? | Custom
|  | AAFP Staff | View a contact's "Individual Type" | quickly track whether a contact is a member, non-member, and what specific membership type they are | To be determined by AAFP | ? | ?
|  | AAFP Staff | Identify any active or past memberships for a contact | track the membership journey of a contact | There is a related list called Subscriptions on the Contact record that details all active and inactive journal subscriptions. Note: this related list will also include journal subscriptions | High | Configuration
|  | AAFP Staff | View a contact's years of consecutive membership as an Active member | to be able to determine qualification for Life membership | To be determined by AAFP | ? | Custom
|  | AAFP Staff | View a contact's years of non-consecutive membership as an Active member | ? | To be determined by AAFP | ? | Custom
|  | AAFP Staff | View a contact's Journal Subscriptions | review a contact's subscriptions with related fulfillment information | There is a related list called Subscriptions on the Contact record that details all active and inactive journal subscriptions. Note: this related list will also include membership information | High | Configuration
|  | AAFP Staff | View a contact's Committee Membership | review a contact's participation in commission, Member Interest Groups, and other groups | There is a related list called Commnity Group Members on the Contact record that details all commissions, MIGs, and other group affiliations related to a contact | High | Configuration
|  | AAFP Staff | View a contact's Receipts | review a list of past sales and refunds | There is a related list called Receipts on the Contact record that details all of a customer's receipts | High | Configuration
|  | AAFP Staff | View a contact's Invoices | review a list of open and closed invoices for a customer | There is a related list called Invoices on the Contact record that details all open and closed invoices | High | Configuration
|  | AAFP Staff | View a contact's Credits | review a list of available credits for a contact | There is a related list called Credit Memos on the Contact record that details any available credits | High | Configuration
|  | AAFP Staff | View a contact's Event attendance | review a contact's historical event history | There is a related list called Events on the Contact record that details all event attendance | High | Configuration
|  | AAFP Staff | View a log of outbound emails to the contact | review a contact's interaction with AAFP | There is a related list called Activity History on the Contact record that details all emails sent to a contact | High | Configuration
|  | AAFP Staff | View CME standing | verify their re-election status | Field exists on contact record | High | Integration
|  | AAFP Staff | View CME credits | review prescribed and elective CME credits along with related activity | Can click a button which opens an HTML table to view CME activity with relevant fields | High | Integration

## Membership
User Story ID | Sprint | Theme | As a(n)... | I want to... | So that I can... | Priority | Acceptance Criteria | Size
1 | Sprint 1 | Membership | Physician; Student; Resident | apply for a new AAFP membership | have access to AAFP's CME reporting service, discounts on hundreds of courses and products, and leading-edge career and practice support. | High | There is an web intake form for applicants to provide contact information and medical certifications. | 8

## Events
User Story ID | Sprint | Theme | As a(n)... | I want to... | So that I can... | Priority | Acceptance Criteria | Size
|  | Events | AAFP Admin | create a complex event | sell tickets and individual sessions to registrants at various price points and display information regarding speakers, venues, sessions, and event details. | High | There is an interface for creating complex events with various tickets, price rules, speakers, and venues. | 2

## Chapters
User Story ID | Sprint | Theme | As a(n)... | I want to... | So that I can... | Priority | Acceptance Criteria | Size
|  | Reporting | Chapter Leader | access a report with a list of Chapter members specific to state whose membership is expiring in the next 60 days. | monitor soon-to-be lapsed members and send follow up communication. | Medium | There is a report accessible in the Chapter portal displaying a dynamic list of members per state whose membership is expiring in the next 60 days. | 1

## API Integration
User Story ID | Sprint | Theme | Effected Fonteva Module(s) | Inbound to SF/Outbound from SF | As a(n)... | I want to... | So that System can... | Detailed Notes | Priority | Assumptions/Preconditions | Acceptance Criteria | Size | Questions?
|  | Integration | Contacts | Outbound from SF | API Admin User | send Member Information like name,address,phone number and demographic information to EDW in a batch at desired intervals. I want to be informed about the failure and success of the process and allow retries on failure. | Synchronize data from Salesforce to EDW | Options - * Salesforce Connect (Real time) * Custom ETL tool. * Appexchange App that accomplishes this. |  |  | * Data extracted and loaded in EDW. * Failure indication. * Retry Mechanism manual or automated. |  | * Does demographic and membership data live on Contact? * Which option they want to go with?
|  | Integration | Contacts | Inbound to SF | API Admin User | create Webservice endpoint for retrieving member information from SF using Salesforce or Spark API's | send real time Member Information like name,address,phone number and demographic information to EDW/Other third party systems when they send Unique Id of Member to SF. |  |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call.* * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Volume <5000 per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | * Estimate of type of data/object fields so can decide if multiple or 1 call is needed?What is demographic info and where its stored in there database, is it coming from multiple tables?Do you need real time?
|  | Integration | Membership | Inbound to SF | API Admin User | create Webservice endpoints for retrieving membership information from SF using Salesforce or Spark API's | send real time Membership Information to other systems when they send Unique Id of Member to SF. |  |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Functionality/Code to pull data to Contact from membership so that they can be clubeed in contact web service? Do you need separate web service for contact and subscription?
|  | Integration | Contact & Accounts | Inbound to SF | API Admin User | create Webservice endpoint for retrieving countries list from SF | send Countries list to other systems when they send JSON request. | There is no Countries Object in Salesforce, we can enable State, Country Picklist feature of Salesforce or create custom field to support this web service. |  | * * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Volume <1000 per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Estimate of type of data/object fields so can decide if multiple or 1 call is needed? Outbound also?
|  | Integration | Contact & Accounts | Inbound to SF | API Admin User | create Webservice endpoints for retrieving states of a particular country from SF | send States list to other systems when they send Country name to SF. | Retrieval of Countries and States can be done in one Api if the Response size is not large. We can enable State, Country Picklist feature of Salesforce or create custom fields to support this web service. |  | * Hierarchical Relationship exists between State and Country * REST/JSON (If using Spark API’s) * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Volume <1000 per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Do they use ISO code or want straight State,country?
|  | Integration | Events | Inbound to SF | API Admin User | create Webservice endpoints for retrieving all active events from SF | send active Events information to other third party systems. |  |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Volume <1000 per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Do they need Ticket type,sessions,speakers and venue information too or just Event information with start and end date?
|  | Integration | Membership/Store | Inbound to SF | API Admin User | create Webservice endpoints for retrieving product or item information from SF using Salesforce or Spark API's | send Product Information to other systems when they send access url of the product to SF. | Real time is not preferrable if large data. Can the Product information be synched one time and than stored in the corresponding database or EDW? |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Large volume of data per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | What is an access url, some unique url that can be created as a field in SF? Can one access URL be on multiple products?
|  | Integration | Membership/Store | Inbound to SF | API Admin User | create Webservice endpoints for retrieving product or item information from SF using Salesforce or Spark API's | send Product Information to other systems when they send product code to SF. | Real time is not preferrable if large data. Can the Product information be synched one time and than stored in the corresponding database or EDW? |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Large volume of data per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Unique Product code?
|  | Integration | Membership/Store | Inbound to SF | API Admin User | create Webservice endpoints for retrieving product or item information from SF using Salesforce or Spark API's | send Product Information to other systems when they send product name to SF. | Real time is not preferrable if large data. Can the Product information be synched one time and than stored in the corresponding database or EDW? |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Large volume of data per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Unique product name?
|  | Integration | Membership/Store | Inbound to SF | API Admin User | create Webservice endpoints for retrieving price from SF using Salesforce or Spark API's | send Product Information to other systems when they send product name to SF. | Real time is not preferrable if large data. Can the Product information be synched one time and than stored in the coressponding database or EDW? |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Large volume of data per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism.
|  | Integration | Membership/Store | Inbound to SF | API Admin User | create Webservice endpoints for retrieving price from SF using Salesforce or Spark API's | send Price Information to other systems when they send product category code to SF. | Real time is not preferrable if large data. Can the Product information be synched one time and than stored in the coressponding database or EDW? |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Large volume of data per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | What is category code, is it some kind of grouping? Price can be dependent on other factors like if it is a member of not etc so is the category code unique per product?
|  | Integration | Membership/Store | Inbound to SF | API Admin User | create Webservice endpoints for retrieving price from SF using Salesforce or Spark API's | send price Information to other systems when they send product code to SF. | Real time is not preferrable if large data. Can the Product information be synched one time and than stored in the coressponding database or EDW? |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Large volume of data per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism.
|  | Integration | Membership/Store | Inbound to SF | API Admin User | create Webservice endpoints for retrieving price from SF using Salesforce or Spark API's | send Price Information to other systems when they send product name/Price key to SF. |  |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Large volume of data per day | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Detail on price from price wizard? Is it same as getting price when product code is sent? Also memebrs can have different price based on some conditions so all parameters will be sent and will also live in SF?
|  | Integration | Contacts | Inbound to SF | API Admin User | create Webservice endpoints for retrieving certifcate of customer/Contact in SF using Salesforce or Spark API's | create ABFM Certificate record associated to the Customer/Contact. |  |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. *Daily is less than 1000 so can be done real time | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Idea of Certficate fields so we can decide what objects are involved?Many certifiicates than can be associated to the contact record?Community Group Members and not an actual certificate?
|  | Integration | Contacts | Inbound to SF | API Admin User | upload/transfer bulk customers certificate records to SF from ABFM | create ABFM certificate records attached to each customer record in SF | Batch process, Data load, bulk APIs? |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. * Large volume of data per day | * Ability to upload bulk data around 100,000 at one time |  | Batch process, bulk apis?
|  | Integration | Contacts | Inbound to SF | API Admin User | create Webservice endpoints for ABFM, AAFP customer match | create record in SF if there is no match, give error? |  |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. *Daily is less than 1000 so can be done real time | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Create record in SF if there is no match, give error?
|  | Integration |  | Inbound to SF | API Admin User | create JWT(JSON Web Token) for API access | can make subsequent calls for API access |  |  |  | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Can use standard salesforce API to retrieve token? If using Spark api's than I have to find out the endpoint to get token.
|  | Integration |  | Inbound to SF | API Admin User | create Webservice endpoint for to Proficiency Testing Post order | Creates invoice based on info from PT Central |  | Need more info? | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * JSON Response size should follow salesforce best practices * Authentication Process Completed. *Daily is less than 1000 so can be done real time | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | Need more info?
|  | Integration | Membership/Store | Inbound to SF | API Admin User | create Webservice endpoint to check For Purchase By Id And URL | send the purchase information per product or individual? Also what kind of Id? |  | send the purchase information per product or individual? Also what kind of Id? |  |  |  | send the purchase information per product or individual? Also what kind of Id?
|  | Integration |  | Inbound to SF | API Admin User | create Webservice endpoints to check for IP Address Authentication | can we use salesforce standard functionalty for ip address range and if not feasible than have to create custom web service end point? |  |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * Not large volume of data * Authentication Process Completed. | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism. |  | can we use salesforce standard functionalty for ip address range and if not feasible than have to create custom web service end point
|  | Shopping Cart Integration | Membership/Store |  | API Admin User | Logged in on Fonteva from there site, possible? Purchase process started in different third party sites so if checkout happens in SF than look and feel will be different. |  |  |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * Not large volume of data * Authentication Process Completed. | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism.
Any outbound API from SF where SF initiates callout like Finance data(Workday)? |  |  |  |  | API Admin User |  |  |  |  | * Hierarchical Relationship between data sent if multiple objects are involved in one Api call. * REST/JSON (If using Spark API’s) * Real Time * Adheres to Salesforce Limits * Not large volume of data * Authentication Process Completed. | * JSON Response sent. * Failure Mechanism - Appropriate HTTP Error code in JSON Response. * Retry Mechanism.
Inbound or Outbound?
Who is making a call member or Admin?

## SSO
User Story ID | Sprint | Theme | Effected Fonteva Module(s) | Organization | IDP/SP | As a(n)... | I want to... | So that System can... | Detailed Notes | Priority | Assumptions/Preconditions | Acceptance Criteria | Size | Questions?
|  | SSO | Contacts | Higher Logic(committee’s member engagement) |  | Member |  |  | Do they support REST/JSON? What kind of authentication? |  |  | * Data extracted and loaded in EDW. * Failure indication. * Retry Mechanism manual or automated. |  | * Does demographic and membership data live on Contact? * Which option they want to go with?
|  |  | Events | FMX OnDemand(A-Z Integration) |  |  |  |  | Do they support REST/JSON? What kind of authentication?A-Z is only for exhibitors and sponsorships
|  |  | Membership | Ethos LMS |  |  |  |  | Do they support REST/JSON? What kind of authentication?
|  |  |  | SoftLink |  |  |  |  | Do they support REST/JSON? What kind of authentication?
|  |  |  | Workday(Finance) |  |  |  |  | Do they support REST/JSON? What kind of authentication? | Push data to workday/ not sure about coming back to SF
|  |  |  | EDW(Datawarehouse) |  |  |  |  | SF will push data to warehouse, read also? Any API are we creating to support that? GET or POST?Do they support REST/JSON? What kind of authentication?
|  |  |  | CDYNE(Address Validation) |  |  |  |  | Latitude,longitude and address validation - any SSO needed or just callout made to CDNE from SF? When should the callout be made?Do they support REST/JSON? What kind of authentication?
|  |  |  | CME(Continuing Medical Education) |  |  |  |  | Continuing Medical education(CME has 50 Million data) - HTML content from outside salesforce server, make api call use iframe in SF to show that. What point in the process will this happen? When should be the callout made? NO SSO I think just callout from SF? Do they support REST/JSON? What kind of authentication?
|  |  |  | AD/Azure for staff. |  |  |  |  | Does Fonteva have anything to do with this?
|  |  |  | Configuration for Social Login in SF |  |  |  |  | Facebook etc?
|  |  |  | SF is IDP for members/customers |  |  |  |  | Around how many members total for both?
Desktop Integration where staff user sign in on dektop and gets logged in to all systems.ADFS – windows credentials to login.Active Directory FS
|  |  |  | Website |  |  |  |  | any SSO?
|  |  |  | Archive |  |  |  |  | ETL process between EDW and SF, Salesforce Connect?
shopping cart integration?